## Security Control Matrix
Control Family | Control ID | Control Name | Control Description | UH Policy Alignment (EP 2.214) | UHCC Implementation Status | NSPM-33 / NIH Relevance | MFA/Phishing-Resistant Required | Ransomware Recovery Task | Responsible Party (ISSM/ITS/PI) | Review Date | Comments/Evidence
Access Control | AC-2 | Account Management | Manage system accounts (create, activate, modify, disable, and remove). | Section 3.1: Access Control | Pending Audit | Cyber Pillar: Identity Management | Yes | Audit 400 researchers for orphaned accounts. | ISSM / Dept IT | 2026-05-15 | Critical for RCUH/Grad Student offboarding.
Access Control | AC-3 | Access Enforcement | Enforce approved authorizations for logical access to information and system resources. | Section 3.1.2: Least Privilege | Partial | Cyber Pillar: Data Access | Yes | Network segmentation between Lab and Clinical. | UH ITS / ISSM | 2026-06-01 | Isolate Hawaii Tumor Registry SEER data.
Identification & Auth | IA-2 | Identification and Authentication (Org Users) | Uniquely identify and authenticate organizational users. | Section 3.5: Identification and Authentication | In Progress | Cyber Pillar: Authentication | Yes (Yubikey) | Enforce phishing-resistant MFA for all servers. | ISSM | 2026-05-25 | NIH May 2026 RST Certification deadline.
Incident Response | IR-4 | Incident Handling | Implement an incident handling capability for security incidents. | Section 3.6: Incident Response | Implemented (Updated) | Cyber Pillar: Response and Recovery | No | Post-2025 Ransomware Recovery Plan alignment. | UH ITS / ISSM | 2026-04-30 | Validated by UH Information Security Task Force.
System & Comm Prot | SC-7 | Boundary Protection | Monitor and control communications at external and internal boundaries. | Section 3.13: System and Communications Protection | Pending | Cyber Pillar: Network Security | No | Move sensitive servers to UH ITS Data Center. | UH ITS / PI | 2026-07-01 | July 2026 NSPM-33 Deadline.
Configuration Mgmt | CM-8 | Information System Component Inventory | Develop and maintain an inventory of system components. | Section 3.4: Configuration Management | Planned | Cyber Pillar: Asset Management | No | Launch AI Tool Discovery Survey to 400 staff. | ISSM / Lab PIs | 2026-05-30 | Identify 'Shadow AI' and local HPC instances.
Awareness & Training | AT-2 | Security Awareness Training | Provide basic security awareness training to system users. | Section 3.2: Awareness and Training | In Progress | Training Pillar: Mandatory RST | No | 100% completion of ISAT and RST modules. | All Staff / RCUH | 2026-05-25 | Required for all NIH Key Personnel.
Contingency Planning | CP-9 | System Backup | Conduct backups of user-level and system-level information. | Section 3.8: Contingency Planning | High Priority | Cyber Pillar: Recovery | No | Immutable backups for historical epidemiology data. | UH ITS / PI | 2026-06-15 | Direct response to August 2025 breach.
Audit & Accountability | AU-2 | Event Logging | Determine that the system is capable of generating audit records. | Section 3.3: Audit and Accountability | Implementing | Cyber Pillar: Monitoring | No | Deploy 24/7 endpoint monitoring on 400 devices. | UH ITS (SOC) | 2026-07-01 | Mandated by UH President post-breach.
Maintenance | MA-3 | Maintenance Tools | Approve, control, and monitor maintenance tools. | Section 3.7: Maintenance | Planned | Cyber Pillar: Tool Integrity | No | Audit AI model training tools (Koa/Mana clusters). | ISSM / CI Team | 2026-08-01 | Ensure local AI tools don't exfiltrate data.

## AI Correlation Inventory
Lab/Department | PI Name | AI Tool Name | Version/Deployment (Web/Enterprise/Local) | Data Classification (EP 2.214) | Data Type (Clinical/Genomic/Admin) | User Groups (UH/RCUH/Foreign) | Risk Tier (1-3) | Compliance Status (Approved/Pending/Prohibited) | DSR/Security Review ID | NIST 800-171 Controls | NSPM-33 Pillar | MFA Status (Phishing-Resistant) | Storage Location (ITS Data Center/Local) | Last Audit Date | Review/Renewal Date | Notes
Epidemiology | Dr. Smith | ChatGPT (Public) | Web Browser | Sensitive (PII) | Grant Writing | UH Faculty | Tier 3 | Approved |  | 3.1.1, 3.5.3 | Training | Yubikey |  | 2026-04-30 | 2027-04-30 | No regulated data entry allowed.
Clinical Trials Unit | Dr. Jones | Local Llama 3 | On-prem (HPC Koa) | Regulated (HIPAA) | Patient Trial Data | UH/RCUH Staff | Tier 1 | Pending | DSR-2026-001 | 3.1.1, 3.1.2, 3.10.1 | Cyber | Yubikey | ITS Data Center | 2026-04-30 | 2026-10-30 | Air-gapped instance; no external API calls.
Genomics Lab | Dr. Lee | BioGPT | Enterprise (BAA) | Sensitive (Proprietary) | Genomic Sequences | Grad Students | Tier 2 | Approved | SR-8842 | 3.4.1, 3.13.1 | Export Control | Duo | Cloud (Vetted) | 2026-04-30 | 2027-04-30 | Requires BAA for "No-Training" clause.
Administrative Office | M. Tanaka | Microsoft Copilot | Enterprise (UH Managed) | Restricted | Meeting Notes/Schedules | All Staff | Tier 3 | Approved | Enterprise License | 3.1.1 |  | Duo | OneDrive | 2026-04-30 | 2027-04-30 | Standard UH Enterprise deployment.